## Daily Plan
Day | Week | Phase | Feature | Build / Focus | Test / Acceptance Check | End-of-Day Deliverable | Time | Status | Notes
1 | 1 | Foundation | Project architecture | Define modules, boundaries, API/service structure | Review future modules fit without circular dependencies | Architecture notes | 1h | Done | Architecture notes at docs/ARCHITECTURE.md. No fuller PRD doc exists in repo (docs/PRD.md is a changelog) so module responsibilities were inferred from Daily Plan phases; re-check if a real PRD surfaces.
2 | 1 | Foundation | Repo + tooling | Set up Next.js/TypeScript, linting, formatting, env handling, Git workflow | Fresh install + lint + build | Clean starter repo | 1h | Done | Next.js 16 (Turbopack) + TS + ESLint scaffolded, plus Prettier, Husky pre-commit (lint-staged), .env.example, README with git-workflow notes. lint/build verified locally.
3 | 1 | Foundation | Automated testing setup | Set up a unit/API test runner and one end-to-end test tool | One passing sample test of each kind runs locally | Test harness ready | 1h | Done | Vitest for unit/API tests (sample: src/modules/kernel/health.ts + its route), Playwright for E2E (e2e/health.spec.ts). Playwright configured with channel: chrome (system Chrome) because this sandbox cannot download the bundled Chromium binary over the network (CDN request timeout) - verified passing locally against system Chrome; CI will need Chrome available on the runner (ubuntu-latest/windows-latest images ship it) or a switch to bundled chromium download.
4 | 1 | Foundation | Database | Set up PostgreSQL + Prisma | Migration works on clean DB | DB connected | 1h | Done | Prisma 7 + PostgreSQL wired up via the pg driver adapter (schema.prisma has no url field in Prisma 7 - connection lives in prisma7.config.ts + the adapter). Local dev DB is npx prisma dev (embedded PGlite Postgres, no Docker needed - Docker Desktop would not start in this sandbox). Note: PGlite does not support native extensions (pgcrypto attempt failed) - stick to Prisma-side ID generation (uuid()/cuid()), not DB extensions, for portability. Kernel db client (src/modules/kernel/db.ts) added with a passing automated test that runs a real query against the live dev DB. No domain models yet - that is Day 5.
5 | 1 | Foundation | Core schema | Create Organisation, Department, User, Role base models. Design as multi-tenant-ready (org_id scoping on every table) even though only one organisation exists today — cheap insurance if this is ever sold to other firms. | Create/read sample records | Initial migration | 1h | Done | Organisation, Department, Role, User models in prisma/schema.prisma (migration 20260918094921_core_schema). Organisation is the tenant root (no org_id on itself); Department/Role/User all carry organisationId with cascade delete, plus a unique(organisationId, name/email) constraint. IDs are Prisma-generated UUIDs (not a DB extension - see Day 4 note). department/roleId on User are nullable at the DB level; Day 20 (Create employee) will decide whether to require them at the validation layer. 5 automated tests in src/modules/identity/schema.test.ts cover create/read, relations, duplicate-name rejection, and cascade delete.
6 | 2 | Foundation | Validation + errors | Create shared validation and API error conventions | Invalid payloads return predictable errors | Validation/error layer | 1h | Done | Shared ApiError class + toApiErrorResponse() (src/modules/kernel/errors.ts) map ApiError/ZodError/unknown errors to one predictable {error:{code,message,details?}} JSON shape. zod is the standard validation library. Reference implementation wired into a new POST /api/health/echo route (validate-then-respond pattern every future route copies). 6 automated tests cover valid payload, validation failure, and malformed JSON.
7 | 2 | Foundation | UI shell | Build app shell, sidebar, header, responsive layout | Desktop + mobile smoke test | Reusable app shell | 1h | Done | AppShell component (src/components/AppShell.tsx): sticky header + off-canvas sidebar nav, CSS-media-query responsive (sidebar always visible >=768px, toggled via a menu button below that). Replaced the default create-next-app starter homepage. Also fixed a real flakiness bug found while testing this: Vitest running test files in parallel was destabilizing the PGlite dev DB connection (fileParallelism disabled + pool max + explicit in db-touching tests - see dev_environment memory). Playwright desktop+mobile viewport smoke test in e2e/app-shell.spec.ts, both passing.
8 | 2 | Foundation | Observability | Add structured server logs and error logging | Trigger test error and verify useful log | Logging baseline | 1h | Done | Structured JSON logging via pino (src/modules/kernel/logging.ts, pino-pretty in dev only). Wired into the shared error handler from Day 6: toApiErrorResponse() logs unexpected errors at error level (with the full error object) and handled ApiErrors at warn level (code + status, no stack noise) - so every route that already follows the Day 6 convention gets logging for free with no extra code. 2 automated tests: one verifies pino emits a structured JSON line with level/time/msg/fields, one verifies the error handler actually calls the logger on an unexpected error.
9 | 2 | Foundation | Seed data | Create repeatable development seed | Seed from empty DB successfully | Seed script | 1h | Done | Idempotent seed (prisma/seed-data.ts: seedDatabase(), all upserts) seeding one organisation, 3 departments, 3 roles, 1 owner user. Wired via prisma7.config.ts migrations.seed using tsx (plain node --experimental-strip-types could not resolve the @/* tsconfig path alias). npm run db:seed -> prisma db seed. Verified idempotent by running twice locally with no errors/duplicates. 2 automated tests (prisma/seed-data.test.ts) cover the happy path and re-running without duplication.
10 | 2 | Foundation | CI pipeline | Add a CI workflow that runs lint + automated tests on every push | A deliberately broken test fails the pipeline; a passing one goes green | Continuous integration baseline | 1h | Done | .github/workflows/ci.yml: on push/PR to any branch, a Postgres 16 service container, npm ci, prisma migrate deploy, lint, typecheck, format:check, vitest, build, then Playwright e2e (ubuntu-latest ships Chrome, matching the channel:"chrome" config from Day 3). YAML validated locally. The literal acceptance check (a deliberately-broken test fails the pipeline, a passing one goes green) needs an actual push to github.com/SakshiK2503/ai-firm-management to observe - the repo has a configured origin remote but nothing has been pushed yet this session; flagged to the founder rather than pushed without asking.
11 | 3 | Auth & Security | Authentication | Implement login | Valid/invalid/empty credentials | Working login | 1h | Done | Password login: User.passwordHash + a DB-backed Session model (org_id-scoped, revocable - not a stateless JWT, per human-override-always-wins). Kernel owns session/password primitives (bcryptjs hashing, NextRequest/NextResponse-based cookie helpers - deliberately not next/headers cookies() so it stays unit-testable outside a real request). Identity owns the login() service. POST /api/auth/login + GET /api/auth/me + a real /login page (UI, not just API - Definition of Done asks for both where applicable). Known simplification: login looks up by email globally, not org-scoped, since only one org exists (flagged, not a real multi-tenant flow). 9 automated tests (password hashing, login service, both routes) + 2 new Playwright E2E cases (valid login redirects, invalid login shows an error). CI updated to seed the DB before running e2e.
12 | 3 | Auth & Security | Sessions | Session persistence + logout | Refresh and logout tests | Stable sessions | 1h | Done | Sliding session expiry: getCurrentUser() + refreshSession() extend a valid session another full 7 days on each /api/auth/me check, and the cookie is re-attached with the new expiry - so an active session does not expire mid-use. POST /api/auth/logout deletes the session row and clears the cookie (idempotent - logging out twice does not error). AppShell now shows a Log out button when signed in; fixed a real bug found while testing it - AppShell lives in the root layout so it never remounts on client-side nav from /login to /, so its one-time auth check never re-ran after signing in (fixed by re-running the check on every pathname change). 8 new automated tests (session lifecycle, refresh-on-check, logout) + 2 new Playwright E2E cases (refresh keeps you logged in, logout actually invalidates the session server-side).
13 | 3 | Auth & Security | Route protection | Protect app routes | Logged-out direct URL blocked | Protected routes | 1h | Done | Protection lives in Server Components, not middleware: Prisma pg driver needs the Node.js runtime, not Edge, which is what middleware runs in by default. A (protected) route group + layout (src/app/(protected)/layout.tsx) calls requireUser() (redirect to /login if no valid session) and renders AppShell; /login is a sibling outside the group and redirects to / if already logged in. AppShell simplified to take userName as a prop from the server layout instead of self-polling /api/auth/me (removes the Day 12 pathname-effect workaround entirely). 2 new Playwright E2E cases for the actual acceptance check (logged-out direct URL blocked; logged-in visiting /login bounces to /). Spent a long stretch chasing what looked like a route-protection bug that was actually prisma dev (PGlite) crashing/losing data under sustained session load - confirmed via curl + the browser tool that the auth/redirect logic itself was correct throughout. Also dropped Playwright to workers:1 (same fix as Vitest fileParallelism:false) - real logins/navigations from parallel workers were their own separate source of flakiness against PGlite.
14 | 3 | Auth & Security | RBAC model | Define role-permission matrix | Matrix reviewed against product roles | RBAC design | 1h | Done | Reviewed by founder and revised (docs/RBAC.md Founder review section has the full diff/reasoning): (1) roles are now data - a Permission catalog (code) + RolePermission join table (DB, seeded by prisma/rbac-seed-data.ts) - enforcement will query roleHasPermission() and never branch on a role name, so adding a role later is a data change not a code change; (2) named the collapse of a fuller 5-tier PRD hierarchy into 3 roles as a conscious simplification (Partner absorbs Super Admin + Department Head); (3) client visibility scoped to assigned-only for Preparer (flagged as a known gap pending Client/Task tables); (4) task:delete replaced with task:cancel (soft/auditable, no material action disappears); (5) client:manage split into editContact (Manager+) vs editStructural (Partner-only); (6) auditLog:view made explicitly the only audit permission that will ever exist for anyone. 15 automated tests total (was 7) covering catalog integrity, grant hierarchy, and DB-integration (seeded grants actually resolve correctly via roleHasPermission).
15 | 3 | Auth & Security | RBAC enforcement | Implement permission middleware | Allowed/denied actions behave correctly | Permission checks | 1h | Done | requirePermission(request, permission) (src/modules/kernel/rbac/enforce.ts): the one enforcement primitive every protected route calls - 401 if no session, 403 if the role lacks the permission (never checks a role name). GET /api/organisation is the reference implementation (Partner-only, since organisation:manage is Partner-only per Day 14). Seed data now has 3 sample users (owner=Partner, manager=Manager, preparer=Preparer, same dev password) specifically so allowed/denied behavior is actually testable, not just theoretical. 8 new unit/API tests + 1 new Playwright E2E test (login as Partner -> 200, login as Manager -> 403) prove real allow/deny behavior end-to-end, not just the permission matrix in isolation.
16 | 4 | Auth & Security | Security baseline | Secrets/env/security headers baseline | No secrets exposed client-side | Security baseline | 1h | Done | server-only guard on session.ts (the one module thats genuinely Next-app-exclusive - db.ts and password.ts stay unguarded on purpose since prisma/seed-data.ts legitimately imports them outside the app; db.ts already has strong inherent protection since @prisma/client+pg depend on Node net/tls that cannot bundle into a browser build anyway). Security headers (X-Content-Type-Options, X-Frame-Options, Referrer-Policy, Permissions-Policy, HSTS) via next.config.ts headers() - verified live via curl and a new Playwright test. A real Content-Security-Policy is explicitly deferred to the Audit & Security hardening phase (Day 131+), not attempted here - a wrong CSP silently breaks fonts/hydration and deserves its own day, not a guess bolted onto a 1-hour baseline day. New npm run verify:no-secrets script scans the actual built client bundle (.next/static) for the real DATABASE_URL value - wired into CI right after the build step. Also found and fixed a real bug while building this: the server-only npm package breaks under both Vitest (fixed via a resolve.alias to a no-op shim) and tsx-run scripts (fixed by not guarding files scripts legitimately need) - see dev-environment memory.
17 | 4 | Organisation | Departments | Create department | Required fields + duplicate prevention | Department creation | 1h | Done | POST /api/departments + department.service.ts createDepartment(). Duplicate prevention comes free from the Day 5 @@unique([organisationId, name]) constraint - the service just maps the P2002 into a clean 409 CONFLICT (new shared src/modules/kernel/db-errors.ts helper, reusable for every future unique-constrained resource). department:manage is Partner-only per Day 14s matrix.
18 | 4 | Organisation | Departments | Department list/search | Search + empty state | Department list | 1h | Done | GET /api/departments (?search=, ?includeInactive=) + listDepartments(). Built the whole Departments admin page (create+list+search+edit/disable) as one screen rather than a create-only page on Day 17 alone, since that is how a real admin UI would actually be laid out - founder pre-authorized batching multiple days when it does not add risk.
19 | 4 | Organisation | Departments | Edit/disable department | Disabled dept cannot receive new work | Department lifecycle | 1h | Done | PATCH /api/departments/[id] (rename and/or isActive toggle) + updateDepartment(), 404s if the department does not exist or belongs to a different org (org-scoping enforced, not just filtered). Disable/enable both verified via API tests, service tests, and E2E. Note on the acceptance check wording ("disabled dept cannot receive new work"): nothing currently assigns work to a department (no Task table, Employee creation is Day 20, not yet built at this point) - deferred the actual guard to Day 20s employee-creation validation, which is next.
20 | 4 | Organisation | Employees | Create employee | Validation + role/department assignment | Employee creation | 1h | Done | POST /api/employees + employee.service.ts createEmployee(). department/role assignment required (not nullable at the validation layer, even though the DB column allows null - Day 5s deferred decision). Closes the Day 19 gap: creating an employee in a disabled department is rejected (400 DEPARTMENT_DISABLED). employee:manage is Partner-only; employee:view (list/detail) is Manager+Partner per Day 14s matrix. Responses use Prisma select (not include) so passwordHash is never even fetched, not just stripped after the fact.
21 | 5 | Organisation | Employees | Employee list/search/filter | Active/inactive filters | Employee directory | 1h | Done | GET /api/employees (?search= by name/email, ?includeInactive=) + listEmployees(). Employees admin page shows the list to Manager+Partner but only shows the create form to Partner (employee:manage) - built as one screen with Day 20/22/23 rather than 4 separate pages, same reasoning as Departments.
22 | 5 | Organisation | Employees | Employee detail | Role, department, manager visible | Employee profile | 1h | Done | GET /api/employees/[id] + /employees/[id] detail page: name/email/department/role/status all visible and resolved (not raw IDs). Manager field intentionally shows "Not tracked yet" rather than a fake value - the managerId/reporting-hierarchy schema field does not exist until Day 24, which is next.
23 | 5 | Organisation | Employees | Edit employee | Changes persist safely | Employee editing | 1h | Done | PATCH /api/employees/[id] + inline edit form on the detail page (rename, reassign department/role, toggle active). Reassigning to a disabled department is rejected the same way creation is. 23 new unit/API tests + 3 new Playwright E2E tests across Days 20-23 (Partner creates+views+edits via the UI; Manager sees the list but not the create form; Preparer is fully blocked).
24 | 5 | Organisation | Hierarchy | Manager/reporting relationship | Prevent invalid self-reporting | Reporting structure | 1h | Done | Migration adds self-referential managerId/manager/directReports on User (nullable - not every employee has a manager). employee.service.ts: assertManagerAssignable() rejects an unknown/cross-org manager, direct self-management (managerId === own id), and any longer cycle (walks up the proposed manager's own chain looking for the employee being updated). Wired into both createEmployee (optional managerId) and updateEmployee (managerId?: string ¦ null - null clears it, omitted leaves it untouched). Employee detail page now shows the real manager (replacing Day 22's "Not tracked yet" placeholder) with a link to their profile, plus a manager select on both the create and edit forms. 6 new unit/service tests (assign, clear, unknown manager, self-management, 2-node cycle, 3-node cycle) + 3 new API route tests + 1 new Playwright E2E test (assign a manager, then verify a cycle attempt is rejected with the correct message).
25 | 5 | Organisation | Skills | Employee skill master | Create/edit skills | Skill records | 1h | Not Started
26 | 6 | Organisation | Skills | Employee skill assignment | Skill level/experience stored | Skills matrix | 1h | Not Started
27 | 6 | Organisation | Availability | Leave/availability model | Unavailable employee rules enforced | Availability baseline | 1h | Not Started
28 | 6 | Client Management | Client master | Create client/group | Required fields + duplicate handling | Client creation | 1h | Not Started
29 | 6 | Client Management | Client master | Client list/search | Search/filter/pagination | Client directory | 1h | Not Started
30 | 6 | Client Management | Client master | Client detail | Overview loads correctly | Client profile | 1h | Not Started
31 | 7 | Client Management | Client master | Edit/activate/deactivate client | Inactive-client rules enforced | Client lifecycle | 1h | Not Started
32 | 7 | Client Management | Entities | Create legal entity | Entity linked to correct client | Entity creation | 1h | Not Started
33 | 7 | Client Management | Entities | Entity list/detail | Multiple entities display correctly | Entity management | 1h | Not Started
34 | 7 | Client Management | Contacts | Create/edit client contact | Validation + duplicate handling | Contact management | 1h | Not Started
35 | 7 | Client Management | Engagements | Create client-service engagement | Service linked to entity/client | Engagement baseline | 1h | Not Started
36 | 8 | Client Management | Client context | Client instructions/responsibility | Instructions visible to authorised users | Persistent client context | 1h | Not Started
37 | 8 | Service Master | Services | Create service | Required service metadata | Service creation | 1h | Not Started
38 | 8 | Service Master | Services | Service hierarchy/categories | Parent-child hierarchy works | Service catalogue | 1h | Not Started
39 | 8 | Service Master | Services | Edit/disable service | Disabled service cannot be newly assigned | Service lifecycle | 1h | Not Started
40 | 8 | Service Master | Configuration | Department + skill requirements | Rules stored/retrieved | Service configuration | 1h | Not Started
41 | 9 | Service Master | Configuration | Standard checklist | Template attaches to service | Reusable checklist | 1h | Not Started
42 | 9 | Service Master | Configuration | TAT/effort/reviewer defaults | Defaults populate correctly | Service defaults | 1h | Not Started
43 | 9 | Service Master | Recurring Work | Recurring service configuration | Generate test recurring instance | Recurring baseline | 1h | Not Started
44 | 9 | Task Engine | Task creation | Create manual task | Client/entity/service validation | Task created | 1h | Not Started
45 | 9 | Task Engine | Task creation | Task ID generation | IDs unique/readable | Task IDs | 1h | Not Started
46 | 10 | Task Engine | Task list | Task list + filters | Status/assignee/client/priority/date filters | Task queue | 1h | Not Started
47 | 10 | Task Engine | Task detail | Task detail workspace | Core and related data load | Task workspace | 1h | Not Started
48 | 10 | Task Engine | Workflow | Status state machine Implement the full PRD state model (New → AI Processing → Awaiting Allocation → Assigned → In Progress → Awaiting Client/Internal Dependency → Submitted for Review → Review in Progress → Correction Required/Approved → Client Delivery → Completed → Archived; separate Cancelled). | Invalid transitions blocked Every valid transition is allowed; every invalid transition is blocked and logged. | Deterministic workflow | 1h | Not Started
49 | 10 | Task Engine | Assignment | Assign employee | Only eligible/active users selectable | Assignment | 1h | Not Started
50 | 10 | Task Engine | Assignment | Reassign task | History preserved + permissions | Reassignment | 1h | Not Started
51 | 11 | Task Engine | Dates | Due dates/priorities | Timezone/date validation | Reliable deadlines | 1h | Not Started
52 | 11 | Task Engine | Checklist | Task checklist | Complete/uncomplete persists | Checklist | 1h | Not Started
53 | 11 | Task Engine | Subtasks | Subtasks | Parent-child behavior tested | Subtask support | 1h | Not Started
54 | 11 | Task Engine | Dependencies | Task dependencies | Blocked-task behavior | Dependencies | 1h | Not Started
55 | 11 | Task Engine | Comments | Internal comments | Permissions + timestamps | Comments | 1h | Not Started
56 | 12 | Task Engine | Attachments | Task attachments | Upload/download/access checks | Attachments | 1h | Not Started
57 | 12 | Task Engine | History | Task activity timeline | Important actions recorded | Task history | 1h | Not Started
58 | 12 | Task Engine | Bulk actions | Bulk status/assignment | Permission + partial failure handling | Bulk operations | 1h | Not Started
59 | 12 | Employee Workbench | My Work | My tasks dashboard | Only authorised personal work visible | My Work | 1h | Not Started
60 | 12 | Employee Workbench | My Work | Today/overdue/upcoming views | Correct date buckets | Work queues | 1h | Not Started
61 | 13 | Employee Workbench | Execution | Start task / working state | Transition + timestamp | Task start | 1h | Not Started
62 | 13 | Employee Workbench | Execution | Update progress | Progress persists | Progress updates | 1h | Not Started
63 | 13 | Employee Workbench | Execution | Submit for review | Reviewer queue receives task | Review submission | 1h | Not Started
64 | 13 | Employee Workbench | Execution | Awaiting client information | Task can enter awaiting-client state | Dependency state | 1h | Not Started
65 | 13 | Employee Workbench | Mobile | Responsive task workflow | Core actions usable on mobile | Mobile smoke test | 1h | Not Started
66 | 14 | Review & Quality | Reviewer queue | Review queue | Only assigned review items visible | Review inbox | 1h | Not Started
67 | 14 | Review & Quality | Review | Open task for review | Files/checklist/history available | Review workspace | 1h | Not Started
68 | 14 | Review & Quality | Review | Approve task | Workflow updates correctly | Approval | 1h | Not Started
69 | 14 | Review & Quality | Review | Return for correction | Correction reason required | Correction workflow | 1h | Not Started
70 | 14 | Review & Quality | Review | Correction cycle | Maker fixes and resubmits | Closed-loop review | 1h | Not Started
71 | 15 | Review & Quality | Review | Reviewer notes | Notes visible with audit trail | Review notes | 1h | Not Started
72 | 15 | Review & Quality | Escalation | Second-level approval | Configured services require higher approval | Multi-level review | 1h | Not Started
73 | 15 | Documents & Knowledge | Repository | Document metadata model | Client/task/document links work | Document model | 1h | Not Started
74 | 15 | Documents & Knowledge | Repository | Client document area | Authorised upload/list/download | Client documents | 1h | Not Started
75 | 15 | Documents & Knowledge | Repository | Upload security — malware/virus scan on upload, encryption at rest, document type/size restrictions | Infected/oversized/blocked file types are rejected with a clear reason | Secure document intake | 1h | Not Started
76 | 16 | Documents & Knowledge | Repository | Versioning | Prior versions preserved | Document versions | 1h | Not Started
77 | 16 | Documents & Knowledge | Repository | Categories/tags | Filter by category/type | Document organisation | 1h | Not Started
78 | 16 | Documents & Knowledge | Repository | Metadata search | Search finds correct records | Document search | 1h | Not Started
79 | 16 | Documents & Knowledge | Knowledge | Link communication to task/client | Traceability works | Linked knowledge | 1h | Not Started
80 | 16 | Documents & Knowledge | Retention | Archive rules Define a retention policy per document category (client input/working paper/final/etc.) with legal-hold exceptions. | Archived items remain auditable | Archive baseline | 1h | Not Started
81 | 17 | Time & Economics | Time tracking | Start/stop timer | Duration calculated correctly | Timer | 1h | Not Started
82 | 17 | Time & Economics | Time tracking | Manual time entry | Validation + edit rules | Manual time | 1h | Not Started
83 | 17 | Time & Economics | Time tracking | Time by employee/task | Totals reconcile | Time summaries | 1h | Not Started
84 | 17 | Time & Economics | Costing | Employee cost rate | Historical/effective rate model | Cost-rate model | 1h | Not Started
85 | 17 | Time & Economics | Costing | Task cost calculation | Time × applicable rate | Task costing | 1h | Not Started
86 | 18 | Time & Economics | Costing | Client/service cost | Aggregations reconcile | Client/service costing | 1h | Not Started
87 | 18 | Time & Economics | Profitability | Revenue/billing placeholder model | Revenue linked to engagement | Revenue baseline | 1h | Not Started
88 | 18 | Time & Economics | Profitability | Client profitability | Revenue - cost calculation verified | Profitability | 1h | Not Started
89 | 18 | Deadlines & SLA | Deadline engine | Deadline rules Model three deadline types — statutory, client-committed, internal — each with its own safety-margin logic. | Due dates calculate consistently | Deadline engine | 1h | Not Started
90 | 18 | Deadlines & SLA | SLA | SLA configuration | Service/client SLA rules stored | SLA config | 1h | Not Started
91 | 19 | Deadlines & SLA | Escalations | Overdue detection | Overdue tasks match deadline data | Overdue detection | 1h | Not Started
92 | 19 | Deadlines & SLA | Notifications | In-app notifications | Assignment/deadline/review alerts | Notifications | 1h | Not Started
93 | 19 | Deadlines & SLA | Reminders | Reminder rules | Upcoming/overdue reminders trigger correctly | Reminders | 1h | Not Started
94 | 19 | Deadlines & SLA | Escalations | Manager escalation | Configured threshold triggers escalation | Escalation | 1h | Not Started
95 | 19 | Communication & AI Intake | Governance | AI provider governance — secrets/keys, per-request token/cost budget, rate limits, and a defined fallback (route to manual queue) if the AI service is slow or unavailable | A simulated AI outage still lets a message reach the manual queue; a cost-budget alert fires at threshold | AI governance baseline | 1h | Not Started
96 | 20 | Communication & AI Intake | Communication | Communication data model | Message/channel/sender/time/attachment stored | Communication records | 1h | Not Started
97 | 20 | Communication & AI Intake | Inbox | Internal communication inbox | Messages searchable + traceable | Communication inbox | 1h | Not Started
98 | 20 | Communication & AI Intake | WhatsApp | Integration adapter boundary | Provider contract isolated | WhatsApp adapter | 1h | Not Started
99 | 20 | Communication & AI Intake | AI intake | Structured extraction schema | AI output validates against schema | AI output contract | 1h | Not Started
100 | 20 | Communication & AI Intake | AI intake | Client identification | Known client/entity matching tested | Client matching | 1h | Not Started
101 | 21 | Communication & AI Intake | AI intake | Service/department classification | Maps to service master | Classification | 1h | Not Started
102 | 21 | Communication & AI Intake | AI intake | Deadline/priority extraction | Dates/urgency validated | Deadline extraction | 1h | Not Started
103 | 21 | Communication & AI Intake | AI intake | Attachment understanding | Attachments linked to proposed request | Attachment intake | 1h | Not Started
104 | 21 | Communication & AI Intake | AI intake | Voice-note intake — transcribe WhatsApp voice notes into text before AI extraction | A sample voice note produces a usable transcript and correct downstream extraction | Voice intake | 1h | Not Started
105 | 21 | Communication & AI Intake | AI intake | Confidence scoring | Confidence stored with AI event | Confidence model | 1h | Not Started
106 | 22 | Communication & AI Intake | Human-in-loop | Confirmation queue | Medium/low confidence requires review | Approval queue | 1h | Not Started
107 | 22 | Communication & AI Intake | Task generation | AI result → proposed task | Malformed output cannot create task | AI → task | 1h | Not Started
108 | 22 | Communication & AI Intake | Task generation | Internal AI task creation — employee types a natural-language instruction and it runs through the same AI-extraction → proposed-task flow as WhatsApp/email | A typed instruction produces the same structured task fields as message intake | Internal AI intake | 1h | Not Started
109 | 22 | Communication & AI Intake | Safety | Deterministic AI guardrails | AI cannot bypass permissions/status/cost rules | Guardrails | 1h | Not Started
110 | 22 | Allocation Engine | Capacity | Employee capacity model | Capacity uses availability + planned effort | Capacity model | 1h | Not Started
111 | 23 | Allocation Engine | Eligibility | Eligibility rules | Department/skill/role constraints | Eligible pool | 1h | Not Started
112 | 23 | Allocation Engine | Scoring | Allocation scoring | Factors are deterministic + explainable | Allocation score | 1h | Not Started
113 | 23 | Allocation Engine | Scoring | Workload balancing | Capacity matters more than raw task count | Capacity-aware allocation | 1h | Not Started
114 | 23 | Allocation Engine | Scoring | Deadline/priority weighting | Urgent work affects recommendation | Priority weighting | 1h | Not Started
115 | 23 | Allocation Engine | Scoring | Experience/client responsibility | Relevant context can influence recommendation | Context weighting | 1h | Not Started
116 | 24 | Allocation Engine | Recommendation | Allocation recommendation UI | Manager sees reasons | Recommendation | 1h | Not Started
117 | 24 | Allocation Engine | Assignment | Controlled automatic assignment | Only approved task classes auto-assign | Controlled automation | 1h | Not Started
118 | 24 | Allocation Engine | Override | Human override | Override reason is logged | Override | 1h | Not Started
119 | 24 | Allocation Engine | Reallocation | Redistribution recommendation | Overloaded work can be suggested for redistribution | Reallocation | 1h | Not Started
120 | 24 | Management Command Centre | Dashboard | Organisation overview | Counts reconcile with task data | Executive overview | 1h | Not Started
121 | 25 | Management Command Centre | Dashboard | Department workload | Department totals reconcile | Department view | 1h | Not Started
122 | 25 | Management Command Centre | Dashboard | Employee workload/capacity | Metrics reconcile | Capacity view | 1h | Not Started
123 | 25 | Management Command Centre | Dashboard | Overdue and at-risk | Risk list matches deadline engine | Risk queue | 1h | Not Started
124 | 25 | Management Command Centre | Dashboard | Review queue metrics | Metrics reconcile | Review metrics | 1h | Not Started
125 | 25 | Management Command Centre | Analytics | Turnaround time | Calculated from lifecycle timestamps | TAT metric | 1h | Not Started
126 | 26 | Management Command Centre | Analytics | Utilisation | Productive/available time calculation | Utilisation metric | 1h | Not Started
127 | 26 | Management Command Centre | Analytics | Rework | Correction cycles/time measured | Rework metric | 1h | Not Started
128 | 26 | Management Command Centre | Analytics | Delay-cause attribution — tag each delay as employee-caused, client-caused, manager/reviewer-caused, or dependency-caused; roll up into analytics | Three seeded delay scenarios each show the correct attributed cause | Delay-cause analytics | 1h | Not Started
129 | 26 | Management Command Centre | Analytics | Client/service economics | Cost/profitability views reconcile | Economics dashboard | 1h | Not Started
130 | 26 | Management Command Centre | Alerts | Exception dashboard | Only actionable exceptions shown | Exception centre | 1h | Not Started
131 | 27 | Audit & Security | Audit log | Central audit event model | Create/update/status/assignment/review actions logged | Audit model | 1h | Not Started
132 | 27 | Audit & Security | Audit log | Audit viewer | Authorised filtering works | Audit viewer | 1h | Not Started
133 | 27 | Audit & Security | Access | Object-level access checks | Unauthorised data is blocked | Access tests | 1h | Not Started
134 | 27 | Audit & Security | Security | Sensitive action logging | Permission changes/overrides logged | Security audit | 1h | Not Started
135 | 27 | Audit & Security | Reliability | Error handling + retries | Transient failures don't duplicate work | Reliability | 1h | Not Started
136 | 28 | Audit & Security | Testing | Full permission regression | Role matrix passes | Security regression | 1h | Not Started
137 | 28 | AI Management Intelligence | Data layer | Analytics-ready operational views | Metrics query consistently | Analytics data layer | 1h | Not Started
138 | 28 | AI Management Intelligence | AI assistant | Natural-language management query | Answers grounded in system data | Management Q&A | 1h | Not Started
139 | 28 | AI Management Intelligence | AI assistant | Overload detection explanation | Factors shown from operational data | Overload insight | 1h | Not Started
140 | 28 | AI Management Intelligence | AI assistant | Deadline-risk explanation | Risk based on deterministic data | Risk insight | 1h | Not Started
141 | 29 | AI Management Intelligence | AI assistant | Client profitability insight | Uses actual cost/revenue data | Profitability insight | 1h | Not Started
142 | 29 | AI Management Intelligence | AI assistant | Redistribution suggestions | Links to capacity data | Reallocation insight | 1h | Not Started
143 | 29 | AI Management Intelligence | Guardrails | Read-only management AI | AI cannot mutate records directly | AI guardrails | 1h | Not Started
144 | 29 | AI Execution Agents | Agent framework | Define agent/tool contract | Tool permissions documented | Agent framework | 1h | Not Started
145 | 29 | AI Execution Agents | Document agent | Document extraction agent | Known test docs extract correctly | Extraction agent | 1h | Not Started
146 | 30 | AI Execution Agents | Reconciliation agent | Prototype one narrow reconciliation workflow | Compare against known outputs | Reconciliation prototype | 1h | Not Started
147 | 30 | AI Execution Agents | Human review | Agent output → review queue | No finalisation without approval | Agent review | 1h | Not Started
148 | 30 | AI Execution Agents | Audit | Agent action logging | Tool calls/outputs auditable | Agent audit | 1h | Not Started
149 | 30 | AI Execution Agents | Failure handling | Agent timeout/rollback handling | Failed runs don't corrupt task state | Agent reliability | 1h | Not Started
150 | 30 | Client Portal & Delivery | Portal | Client authentication | Client sees only own data | Client auth | 1h | Not Started
151 | 31 | Client Portal & Delivery | Portal | Client request submission | Request creates tracked intake | Client intake | 1h | Not Started
152 | 31 | Client Portal & Delivery | Portal | Client document upload | Upload links to correct request | Client upload | 1h | Not Started
153 | 31 | Client Portal & Delivery | Portal | Pending information view | Outstanding requests visible | Pending docs | 1h | Not Started
154 | 31 | Client Portal & Delivery | Delivery | Deliverable area | Approved deliverables visible | Delivery | 1h | Not Started
155 | 31 | Client Portal & Delivery | Notifications | Client status notifications | Configured events notify client | Client notifications | 1h | Not Started
156 | 32 | Integrations & Production | Email | Email intake adapter | Email becomes traceable intake | Email intake | 1h | Not Started
157 | 32 | Integrations & Production | Notifications | WhatsApp outbound adapter | Approved messages audited | Outbound messaging | 1h | Not Started
158 | 32 | Integrations & Production | Files | Object storage | Large files stored safely | Production storage | 1h | Not Started
159 | 32 | Integrations & Production | Search | Global search | Clients/tasks/docs/comms searchable | Global search | 1h | Not Started
160 | 32 | Integrations & Production | Performance | Indexes/query review | Key pages meet target response times | Performance baseline | 1h | Not Started
161 | 33 | Integrations & Production | Testing | Seeded end-to-end demo scenario | Complete request lifecycle works | E2E demo | 1h | Not Started
162 | 33 | Integrations & Production | Testing | Full regression pass | Critical flows pass cleanly | Regression | 1h | Not Started
163 | 33 | Integrations & Production | Deployment | Staging deployment | Staging is reproducible | Staging | 1h | Not Started
164 | 33 | Integrations & Production | Deployment | Production readiness | Secrets/migrations/backups/monitoring verified | Production checklist | 1h | Not Started
165 | 33 | Integrations & Production | Rollout | Pilot with one department | Real usage issues captured | Pilot | 1h | Not Started
166 | 34 | Integrations & Production | Rollout | Fix pilot blockers | Critical issues resolved | Pilot fixes | 1h | Not Started
167 | 34 | Integrations & Production | Rollout | Final release | Release notes + known limitations | Production release | 1h | Not Started

## Feature Tracker
Phase | Feature | Planned Days | Completed Days | Status | Notes
Foundation | Project architecture | 1 | 1 | Done
Foundation | Repo + tooling | 1 | 1 | Done
Foundation | Automated testing setup | 1 | 1 | Done
Foundation | Database | 1 | 1 | Done
Foundation | Core schema | 1 | 1 | Done
Foundation | Validation + errors | 1 | 1 | Done
Foundation | UI shell | 1 | 1 | Done
Foundation | Observability | 1 | 1 | Done
Foundation | Seed data | 1 | 1 | Done
Foundation | CI pipeline | 1 | 1 | Done
Auth & Security | Authentication | 1 | 1 | Done
Auth & Security | Sessions | 1 | 1 | Done
Auth & Security | Route protection | 1 | 1 | Done
Auth & Security | RBAC model | 1 | 1 | Done
Auth & Security | RBAC enforcement | 1 | 1 | Done
Auth & Security | Security baseline | 1 | 1 | Done
Organisation | Departments | 3 | 3 | Done
Organisation | Employees | 4 | 4 | Done
Organisation | Hierarchy | 1 | 24 | Done | Self-referential manager relationship with cycle prevention (see Daily Plan Day 24).
Organisation | Skills | 2 |  | Not Started
Organisation | Availability | 1 |  | Not Started
Client Management | Client master | 4 |  | Not Started
Client Management | Entities | 2 |  | Not Started
Client Management | Contacts | 1 |  | Not Started
Client Management | Engagements | 1 |  | Not Started
Client Management | Client context | 1 |  | Not Started
Service Master | Services | 3 |  | Not Started
Service Master | Configuration | 3 |  | Not Started
Service Master | Recurring Work | 1 |  | Not Started
Task Engine | Task creation | 2 |  | Not Started
Task Engine | Task list | 1 |  | Not Started
Task Engine | Task detail | 1 |  | Not Started
Task Engine | Workflow | 1 |  | Not Started
Task Engine | Assignment | 2 |  | Not Started
Task Engine | Dates | 1 |  | Not Started
Task Engine | Checklist | 1 |  | Not Started
Task Engine | Subtasks | 1 |  | Not Started
Task Engine | Dependencies | 1 |  | Not Started
Task Engine | Comments | 1 |  | Not Started
Task Engine | Attachments | 1 |  | Not Started
Task Engine | History | 1 |  | Not Started
Task Engine | Bulk actions | 1 |  | Not Started
Employee Workbench | My Work | 2 |  | Not Started
Employee Workbench | Execution | 4 |  | Not Started
Employee Workbench | Mobile | 1 |  | Not Started
Review & Quality | Reviewer queue | 1 |  | Not Started
Review & Quality | Review | 5 |  | Not Started
Review & Quality | Escalation | 1 |  | Not Started
Documents & Knowledge | Repository | 6 |  | Not Started
Documents & Knowledge | Knowledge | 1 |  | Not Started
Documents & Knowledge | Retention | 1 |  | Not Started
Time & Economics | Time tracking | 3 |  | Not Started
Time & Economics | Costing | 3 |  | Not Started
Time & Economics | Profitability | 2 |  | Not Started
Deadlines & SLA | Deadline engine | 1 |  | Not Started
Deadlines & SLA | SLA | 1 |  | Not Started
Deadlines & SLA | Escalations | 2 |  | Not Started
Deadlines & SLA | Notifications | 1 |  | Not Started
Deadlines & SLA | Reminders | 1 |  | Not Started
Communication & AI Intake | Governance | 1 |  | Not Started
Communication & AI Intake | Communication | 1 |  | Not Started
Communication & AI Intake | Inbox | 1 |  | Not Started
Communication & AI Intake | WhatsApp | 1 |  | Not Started
Communication & AI Intake | AI intake | 7 |  | Not Started
Communication & AI Intake | Human-in-loop | 1 |  | Not Started
Communication & AI Intake | Task generation | 2 |  | Not Started
Communication & AI Intake | Safety | 1 |  | Not Started
Allocation Engine | Capacity | 1 |  | Not Started
Allocation Engine | Eligibility | 1 |  | Not Started
Allocation Engine | Scoring | 4 |  | Not Started
Allocation Engine | Recommendation | 1 |  | Not Started
Allocation Engine | Assignment | 1 |  | Not Started
Allocation Engine | Override | 1 |  | Not Started
Allocation Engine | Reallocation | 1 |  | Not Started
Management Command Centre | Dashboard | 5 |  | Not Started
Management Command Centre | Analytics | 5 |  | Not Started
Management Command Centre | Alerts | 1 |  | Not Started
Audit & Security | Audit log | 2 |  | Not Started
Audit & Security | Access | 1 |  | Not Started
Audit & Security | Security | 1 |  | Not Started
Audit & Security | Reliability | 1 |  | Not Started
Audit & Security | Testing | 1 |  | Not Started
AI Management Intelligence | Data layer | 1 |  | Not Started
AI Management Intelligence | AI assistant | 5 |  | Not Started
AI Management Intelligence | Guardrails | 1 |  | Not Started
AI Execution Agents | Agent framework | 1 |  | Not Started
AI Execution Agents | Document agent | 1 |  | Not Started
AI Execution Agents | Reconciliation agent | 1 |  | Not Started
AI Execution Agents | Human review | 1 |  | Not Started
AI Execution Agents | Audit | 1 |  | Not Started
AI Execution Agents | Failure handling | 1 |  | Not Started
Client Portal & Delivery | Portal | 4 |  | Not Started
Client Portal & Delivery | Delivery | 1 |  | Not Started
Client Portal & Delivery | Notifications | 1 |  | Not Started
Integrations & Production | Email | 1 |  | Not Started
Integrations & Production | Notifications | 1 |  | Not Started
Integrations & Production | Files | 1 |  | Not Started
Integrations & Production | Search | 1 |  | Not Started
Integrations & Production | Performance | 1 |  | Not Started
Integrations & Production | Testing | 2 |  | Not Started
Integrations & Production | Deployment | 2 |  | Not Started
Integrations & Production | Rollout | 3 |  | Not Started

## Weekly Review
Week | Days | Main Phase(s) | What Should Be Working | Review Questions | Status | Notes
1 | 1-5 | Foundation | Initial migration | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
2 | 6-10 | Foundation | Continuous integration baseline | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
3 | 11-15 | Auth & Security | Permission checks | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
4 | 16-20 | Auth & Security + Organisation | Employee creation | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
5 | 21-25 | Organisation | Skill records | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
6 | 26-30 | Organisation + Client Management | Client profile | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
7 | 31-35 | Client Management | Engagement baseline | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
8 | 36-40 | Client Management + Service Master | Service configuration | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
9 | 41-45 | Service Master + Task Engine | Task IDs | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
10 | 46-50 | Task Engine | Reassignment | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
11 | 51-55 | Task Engine | Comments | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
12 | 56-60 | Task Engine + Employee Workbench | Work queues | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
13 | 61-65 | Employee Workbench | Mobile smoke test | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
14 | 66-70 | Review & Quality | Closed-loop review | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
15 | 71-75 | Review & Quality + Documents & Knowledge | Secure document intake | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
16 | 76-80 | Documents & Knowledge | Archive baseline | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
17 | 81-85 | Time & Economics | Task costing | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
18 | 86-90 | Time & Economics + Deadlines & SLA | SLA config | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
19 | 91-95 | Deadlines & SLA + Communication & AI Intake | AI governance baseline | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
20 | 96-100 | Communication & AI Intake | Client matching | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
21 | 101-105 | Communication & AI Intake | Confidence model | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
22 | 106-110 | Communication & AI Intake + Allocation Engine | Capacity model | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
23 | 111-115 | Allocation Engine | Context weighting | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
24 | 116-120 | Allocation Engine + Management Command Centre | Executive overview | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
25 | 121-125 | Management Command Centre | TAT metric | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
26 | 126-130 | Management Command Centre | Exception centre | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
27 | 131-135 | Audit & Security | Reliability | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
28 | 136-140 | Audit & Security + AI Management Intelligence | Risk insight | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
29 | 141-145 | AI Management Intelligence + AI Execution Agents | Extraction agent | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
30 | 146-150 | AI Execution Agents + Client Portal & Delivery | Client auth | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
31 | 151-155 | Client Portal & Delivery | Client notifications | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
32 | 156-160 | Integrations & Production | Performance baseline | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
33 | 161-165 | Integrations & Production | Pilot | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started
34 | 166-167 | Integrations & Production | Production release | Did every feature built this week pass? What is blocked? What needs refactoring before moving on? | Not Started

## Release Map
Release | Start Day | End Day | Exit Criteria
R0 Foundation | 1 | 16 | Architecture, database, testing/CI, shell, auth and RBAC baseline works.
R1 Core Operations | 17 | 58 | Organisation, clients, services and the full task engine (incl. complete status model) work end-to-end.
R2 Execution | 59 | 80 | Employee workbench, review and secure, versioned documents work.
R3 Time & Deadlines | 81 | 94 | Time tracking, costing, and the three deadline types with safety-margin logic work.
R4 AI Intake | 95 | 109 | Communication (incl. voice notes and internal typed instructions) → AI extraction → human confirmation → task works safely, with AI cost/fallback governance in place.
R5 Intelligent Allocation | 110 | 119 | Capacity-aware allocation recommendations and controlled automation work.
R6 Management & Audit | 120 | 136 | Dashboards, delay-cause analytics, exception alerts, full audit trail and permission regression all work.
R7 AI Management | 137 | 143 | Management questions and operational insights are grounded in system data, read-only.
R8 Agents + Portal + Production | 144 | 167 | Narrow execution agent, client portal, integrations and production rollout are demonstrable.

## How to Use
How to use this workbook
Daily rule | ~60 minutes: 10 min understand → 35 min build → 10 min test → 5 min commit/notes.
Golden rule | Do NOT start the next feature until the current feature passes its acceptance test.
Testing | At minimum: happy path, validation/error case, permission/access case where applicable, and empty state.
Git | Prefer one small commit per completed feature, e.g. feat: add client creation.
Status | Use the dropdown. Mark Blocked rather than silently carrying unfinished work.
Weekly review | At the end of each week, decide: proceed, spend another day stabilising, or change scope.
Timeline | 150 days × ~1 hour/day = roughly 5 months if done daily; longer if you skip days. This is deliberately end-to-end and conservative.
Architecture principle | Deterministic code remains the source of truth for permissions, workflow, deadlines, cost, audit and records. AI assists rather than controls the system of record.

## Progress Dashboard
Metric | Value
Total planned days
Days done
Days in progress
Days blocked
Completion %

## PRD Coverage
PRD Requirement | Current Roadmap | Coverage | What to Add / Change
Product vision: Communication → AI → Tasks → Employees → Review → Delivery → Documents → Costing → Performance → Management Intelligence | Covered across AI Intake, Task Engine, Workbench, Review, Documents, Economics, Dashboards and AI. | Covered | Keep the end-to-end dependency order.
Capture all material work from WhatsApp, email, verbal/manual instructions, notebooks/personal folders | Manual task creation + WhatsApp/email adapters are covered. | Partial | Add explicit internal/voice/manual intake and an organisational policy that material work must become a task.
Multiple configurable departments | Departments are covered. | Covered | Keep department configuration non-hard-coded.
Super Admin / Management / Department Head / Manager-Reviewer / Employee | RBAC + organisation roles are covered. | Covered | Ensure each role's exact PRD permissions are acceptance-tested.
Future Client User / Portal | Client portal is covered late in roadmap. | Covered | Add invoice visibility and billing to portal scope.
Client master with legal entities, contacts, account manager, services, engagement, billing, instructions, history | Clients/entities/contacts/engagement/context are covered. | Partial | Add explicit account manager, billing structure, service history and client analytics to acceptance tests.
Service Master with department, skill, checklist, TAT, effort, reviewer, recurring nature, documents | Covered. | Covered | Add required-document configuration explicitly.
WhatsApp: text, attachments, voice notes, metadata | WhatsApp adapter + attachment understanding covered. | Partial | Explicitly add voice-note ingestion/transcription and message metadata.
AI intake: client, entity, request, department, service, period, deadline, urgency, attachments, complexity, clarification | Most fields covered. | Partial | Add explicit period, complexity estimation and clarification-required output fields.
AI confidence: high auto-create, medium confirmation, low clarification | Confidence + confirmation queue + guardrails covered. | Covered | Acceptance-test all three bands.
Task fields: source, original instruction, AI summary, estimated hours, client/internal SLA, dependencies | Most are covered. | Partial | Add explicit source/original instruction/AI summary and separate client vs internal SLA fields.
Task status model: New → AI Processing → Awaiting Allocation → Assigned → In Progress → Awaiting Client/Internal Dependency → Review → Delivery → Completed → Archived; Cancelled | Simplified state machine exists. | Partial | Replace simplified workflow with the full PRD state model and test every valid/invalid transition.
Allocation: department, skills, authority, client restrictions, experience, capacity, deadlines, complexity, leave, meetings/holidays, continuity | Capacity, eligibility, skills, experience, availability, deadlines, client responsibility covered. | Partial | Add authority, client restrictions, meetings/holidays and task complexity explicitly.
Allocation must use actual available capacity, not task count | Explicitly covered. | Covered | Keep this as a non-negotiable acceptance criterion.
Explainable allocation + human override + reason | Covered. | Covered | Keep audit trail for recommendation and override.
Employee dashboard: today, in progress, upcoming, waiting, correction, client instructions, documents | Core My Work + queues covered. | Partial | Add dedicated client instructions and required-documents views/acceptance tests.
Task workspace: original instruction, AI interpretation, working papers, client communication, review, activity | Most covered. | Partial | Explicitly add working papers and linked client communication as first-class task sections.
Maker-checker with second-level approval | Review + second-level approval covered. | Covered | Test multi-level approval configuration.
Documents: client input, working paper, draft, review copy, final, acknowledgement, communication | Documents/versioning/categories covered generically. | Partial | Add these exact document categories and versioning acceptance tests.
Organisational knowledge search with controlled access | Global search is covered, but AI knowledge retrieval is only implicit. | Partial | Add semantic/AI search over communications/docs/tasks with permission-aware retrieval.
Management dashboard: open, due today, overdue, waiting client, awaiting review, capacity, alerts | Covered. | Covered | Add exact PRD alert types and exception views.
Management AI: overload, redistribution, client behaviour, cost alerts | Covered in AI management intelligence. | Covered | Add the client-behaviour and cost-alert examples as acceptance tests.
Employee performance: distinguish employee/client/manager/dependency-caused delays | Rework/TAT/utilisation covered, but delay attribution is not explicit. | Missing | Add a delay-cause model and analytics before calling performance analytics complete.
Costing: employee hourly cost incl employer cost + overhead, task/service/client/engagement profitability | Cost rate, task/client/service costing and profitability covered. | Partial | Add employer cost + overhead methodology, engagement profitability and department profitability.
Notifications: employee, reviewer, manager, future client | In-app notifications/reminders/escalations covered. | Partial | Add explicit event matrix and future client notification channels.
Internal AI task creation from typed instruction and future voice | Not explicitly in current roadmap. | Missing | Add an internal AI command/intake feature before/alongside WhatsApp intake.
Recurring tasks: monthly/quarterly/annual with calendars | Recurring configuration is covered only as a baseline. | Partial | Add calendar rules, generation, missed-generation recovery and recurrence tests.
Deadline engine: statutory vs client commitment vs internal deadline | Deadline engine exists, but types are not explicit. | Missing | Add three deadline types and safety-margin logic.
Client dependency clock and automatic matching of received documents to requests | Awaiting-client state exists; document intake exists. | Partial | Add dependency timer, pause/resume attribution and incoming-document matching.
Audit trail with complete lifecycle timestamps | Audit model + task history covered. | Covered | Test full lifecycle example from message received to delivery.
Deterministic controls vs AI assistant boundary | Explicitly covered in guardrails. | Covered | Keep as architecture gate before agent work.
Mobile-friendly | Mobile smoke tests covered. | Covered | Keep core employee/reviewer actions usable on mobile.
Core database entities incl Invoice, Notification, AI Event, Audit Log | Most core entities represented conceptually. | Partial | Add explicit Invoice/Billing model and AI Event model if not already present.
Screens: Client Detail tabs include Billing + Analytics; Team Workload; Communication Inbox; Reports; Administration | Most screens are represented indirectly. | Partial | Add screen-level acceptance checklist, especially Client Billing/Analytics tabs and Communication Inbox.
MVP definition | Roadmap deliberately goes beyond MVP into later AI/portal. | Covered | Make Day ~70-90 the production MVP gate, then continue V2+.
Version 2 AI Intake / Version 3 Allocation / Version 4 Client Workflow / Version 5 Cost / Version 6 Management AI | Covered conceptually. | Covered | Preserve version gates.
Future execution agents: reconciliation, extraction, compliance, report prep, research, marketing analytics, communication | Narrow extraction/reconciliation agents are covered. | Partial | Add an extensible agent catalogue and future agent slots; do not implement every agent before validation.
Production rollout: staging, pilot, fixes, release | Covered. | Covered | Keep pilot before full rollout.

## Required Changes
Priority | Change | Why it matters | Recommended timing
P0 | Implement full PRD task status model, including AI Processing, Awaiting Allocation, client/internal dependency, review and delivery states | The current plan simplifies the core workflow and would otherwise miss a major PRD requirement. | Before Task Engine is marked complete
P0 | Add delay-cause attribution: employee/client/manager/dependency | Required for trustworthy performance analytics and management intelligence. | Before Performance Analytics
P0 | Add statutory/client/internal deadline types | Required for the PRD's deadline safety-margin model. | Before SLA/Deadline completion
P0 | Add permission-aware organisational knowledge search / AI retrieval | The PRD explicitly requires searchable institutional memory with controlled access. | Before AI Management Intelligence
P0 | Add voice-note intake/transcription and internal AI task creation | The PRD covers voice notes and internal natural-language task creation. | During AI Intake
P1 | Expand allocation eligibility with authority, client restrictions, meetings/holidays and complexity | These are explicit allocation factors in the PRD. | During Allocation Engine
P1 | Add exact document categories and client/task context metadata | Needed for the intended document/knowledge repository. | During Documents
P1 | Add billing/invoice model and engagement/department profitability | The PRD includes invoices and broader profitability dimensions. | During Economics / Client Portal
P1 | Add recurring calendar generation and recovery | The current recurring baseline is too shallow for the PRD requirement. | During Service/Deadline work
P1 | Add exact screen-by-screen acceptance checklist | Prevents functional coverage gaps hidden behind generic module completion. | During UI implementation
P2 | Expand future agent catalogue beyond extraction/reconciliation | The PRD lists additional future agent categories, but they are explicitly future scope. | After core agents are proven
APPLIED | v2 update: testing framework, CI, multi-tenant-ready schema, upload security/retention, 3 deadline types, AI provider governance, voice-note intake, internal AI task creation, delay-cause attribution added into Daily Plan; Release Map and Feature Tracker regenerated to match (now 167 days / 34 weeks). | Closes the P0/P1 items that were structural (schema/workflow) rather than UI-only. | Done before Day 1